## 项目交接
项目 | 交接人
Forwarder Invoice | Max
Courier Invoice | Max
SPS2.0 | Max
SPS1.0 | Max
Sales Plan | Bin
Group eForm | Bin
AR Settlement Clearing | Max
ORSO | Bin
SOH.LaunchPad | Max
SOH.H&M | Max
OCR_Adidas | Max
VapQuotation | Max

## 任务交接
System | To Do Task | Description | Deadline | 跟进人 | 交接人
SPS2.0 | UQL Projection Upload | 参考PM系统 |  | Cherry Tan | Max
SPS2.0 | Projection | 用户使用Upload方式创建shipment时，不会赋予前置状态，导致Shipment level-“Delete” function的时候，系统找不到上一个status是什么，不要显示Null，需要default “Draft” |  | Cherry Tan | Max
SPS2.0 | Auto Status Report Enh. | 1,目前SPS2.0 的Auto Status Report 是按照sales group分别发送的,有用户要求合并发送 2,Auto Status Report文件的命名方式改为：Sales Group_Status_report_YYY_MM_DD，如：L01_Status_report_2026_05_25 3,目前从Auto Status Report点击下载的报表，表头的日期，Create Date，Last Change Date都是显示下载的当天(image 1),需要改为正确的日期 | 2026-08-28 | Cherry Tan | Max
SPS2.0 | Project Index Issue | Projection Index页面搜索接受系统default 除了Delete以外的其他 status | 2026-08-28 | Cherry Tan | Max
SPS2.0 | Status Report | SPS2.0导出的报表，Factory字段分了bonded 和 non bonded，影响数据分析 Cherry Tan: 报表拿数据的时候，是否可以只拿Code | 2026-09-11 | Cherry Tan | Max
SPS2.0 | ShipmentProjection Report | Shipment Projection Report 添加以下字段 CG, Customs Duty (FVB GSD已添加), Washing Type, Fty Pur Trims-2.0的数据取costing guideline Customer Department Desc修改取值逻辑：Customer Department字段取code，Customer Department Desc字段取Desc 详细内容见PM系统以及FS | 2026-08-21 | Cherry Tan | Max
SPS2.0 | Projection、Update、Upload | SPS2.0 界面添加Classification & ACC ETA以及更新部分Function 详细内容见PM系统以及FS |  | Cherry Tan | Max
SPS2.0 | ShipmentProjection Report | 根据Sales Org导出SPS 1.0的数据-->由于SPS 1.0的Shipment Projection没有根据Sales Org作为条件导出数据， 因此需要在SPS 1.0增加Sales Org作为条件，但不显示在导报表页面 详细内容见PM系统以及FS | 2026-09-11 | Cherry Tan | Max
SPS2.0 | Status Report | Status Report 添加字段 以及部分字段取值逻辑更新 详细内容见PM系统以及FS | 2026-09-11 | Cherry Tan | Max
SPS2.0 | Intimate ShipmentProjection Report | 相关字段取值逻辑更新 FS:https://crystalgroup.sharepoint.com/:x:/r/sites/CISD_FSLib/PRC_SapDev/_layouts/15/Doc.aspx?sourcedoc=%7B0173C929-58A5-4108-9F11-B21F7EDFFEEF%7D&file=SPS2.0-Intimate%20Shipment%20Projection%20Report_issuelog_v202600717.xlsx&action=default&mobileredirect=true |  | Lydia Gao | Bin
Sales Plan | Upload | Sales Plan Item upload – 开发一个新功能，批量上传Sales Plan中Material部分的Item |  | Jassie Zhou | Bin
Sales Plan |  | Item的key值增加Customer Style No和Fabric Mill, 目前时Material + Color相同不允许产生第二条Item, 改成Material + Color+ Customer Style No + Fabric Mill相同不允许产生第二条，并且balance的逻辑需要修改，获取FVB的balance进行分配，具体查看FS 该点还未确认清楚需求，待用户确认清楚需求后开发 |  | Jassie Zhou | Bin
Sales Plan | Eamil | change email format - 待批核和批核邮件格式的修改，具体查看FS 该点还未确认清楚需求，待用户确认清楚需求后开发 |  | Jassie Zhou | Bin
Group eForm | AssetPO | QAS Issues Issues Log:https://crystalgroup.sharepoint.com/:x:/r/sites/CISD_FSLib/PRC_SapDev/_layouts/15/Doc.aspx?sourcedoc=%7B1F493821-B74B-43A3-81FB-3686D6B5327E%7D&file=Issue%20log%20(SIT)%20-%20Fixed%20Asset%20PO.xlsx&action=default&mobileredirect=true |  | Victor Cheung | Max-Bin
Forwarder Invoice | OCR | New OCR 15 Template FS:https://crystalgroup.sharepoint.com/sites/CISD_FSLib/PRC_SapDev/eForm%20for%20SAP/Forms/AllItems.aspx?id=%2Fsites%2FCISD%5FFSLib%2FPRC%5FSapDev%2FeForm%20for%20SAP%2FForwarder%20Invoice%2F2026%2D05%20New%20Template&viewid=104ebe0b%2D94de%2D4572%2Da172%2Dbe70813c5484&newTargetListUrl=%2Fsites%2FCISD%5FFSLib%2FPRC%5FSapDev%2FeForm%20for%20SAP&viewpath=%2Fsites%2FCISD%5FFSLib%2FPRC%5FSapDev%2FeForm%20for%20SAP%2FForms%2FAllItems%2Easpx | 2026-09-15 | Yan Ren | Max
Forwarder Invoice | BD FIV & OCR | BD FIV待开发 FS：https://crystalgroup.sharepoint.com/sites/CISD_FSLib/PRC_SapDev/eForm%20for%20SAP/Forms/AllItems.aspx?id=%2Fsites%2FCISD%5FFSLib%2FPRC%5FSapDev%2FeForm%20for%20SAP%2FForwarder%20Invoice%2F2026%2D05%20BD%20FIV&viewid=104ebe0b%2D94de%2D4572%2Da172%2Dbe70813c5484&newTargetListUrl=%2Fsites%2FCISD%5FFSLib%2FPRC%5FSapDev%2FeForm%20for%20SAP&viewpath=%2Fsites%2FCISD%5FFSLib%2FPRC%5FSapDev%2FeForm%20for%20SAP%2FForms%2FAllItems%2Easpx | 2026-09-15 | Victor Cheung | Max
Courier Invoice | SG CIV eform | FS:https://crystalgroup.sharepoint.com/:x:/r/sites/CISD_FSLib/PRC_SapDev/_layouts/15/Doc.aspx?sourcedoc=%7B9E628A9E-2232-4137-A3B4-E6C85C719912%7D&file=CSLG%20DHL%20Workflow%20%26%20requirement.xlsx&action=default&mobileredirect=true | 2026-11-06 | Victor Cheung | Max