## Plan
Weekly Development Planning Report | [8 empty] | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17
Date: | 2026-07-27 | [7 empty] | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21
[9 empty] | Plan 计划 | [11 empty] | Actual 实际
开发者 | 记录日期 | 所属系统 | SAP 变更号 | 程序名 | 程序功能说明 | 公司 | 跟进人 | 要求人 | 当前周 | 下周1 | 下周2 | 下周3 | 4周后 | 总用时 | 计划开始日期 | 计划完成日期 | 修正后开始日期 | 修正后完成日期 | 修正次数 | 用户要求完成日期 | 之前周累计用时 | 当周用时 | 合计用时 | 完成日期 | 备注 | 功能团队希望开发完成日期 | 是否发包 | 优先级 | FS 齐备日期 | FS 位置 | FS 已确认？ | FS 确认日期
Developer | Report Date | Project ID | CHARM No. | Program Title | Program Description | Initiated Company (Denim, CKL, Sweater, Intimate, LifeStyle) | Requested By | Advised By | This Week | Next Week 1 | Next Week 2 | Next Week 3 | Over 4 Week | Total Man Hrs per Program | Plan Start Date | Plan Completion Date | Revised Start Date | Revised COM Date | No. of times on Revise COM Date | User request Completion Date | Last Week Cumulated Man Hrs | Weekly allocated Man Hrs | Allocated Man Hrs | Actual COM Date | Remark | Functional Team Expected Development Date | Outsource | Priority | F/S ready date | F/S URL | F/S Confirm or Not? | F/S Confirm Date
Min Fei | 2026-07-20 |  |  | Handover | Handover Meeting | Lifestyle | [7 empty] | 2 | 2026-07-20 | 2026-07-24 | [5 empty] | 2 | 2 | 2026-07-24
Min Fei | 2026-07-20 |  |  | CIV | FOB01 Template Update & Excel Extract Error Fixed | Lifestyle | Yuki Li | [6 empty] | 8 | 2026-07-20 | 2026-07-24 | [5 empty] | 8 | 8 | 2026-07-24
Min Fei | 2026-07-28 |  |  | FIV | Invoice Duplication Error Check | Lifestyle | Yan Ren | [6 empty] | 2 | 2026-07-20 | 2026-07-24 | [5 empty] | 2 | 2 | 2026-07-24
Min Fei | 2026-07-20 |  |  | SPS 2.0 | Issues & Error Check | Lifestyle | Cherry Tan | [6 empty] | 6 | 2026-07-20 | 2026-07-24 | [5 empty] | 6 | 6 | 2026-07-24
Min Fei | 2026-07-20 |  |  | Leave | 请假 | Lifestyle |  |  | 8 |  |  |  |  | 8 | 2026-07-27 | 2026-07-31
Min Fei | 2026-05-11 |  |  | Sales Plan | Enh. | Lifestyle | Jassie Zhou | [6 empty] | 48 | 2026-06-08 | 2026-06-26 |  |  |  |  | 16 | 8
Min Fei | 2026-07-13 |  |  | Group eForm | Assets PO Issues | Lifestyle | Victor Cheung |  | 8 |  |  |  |  | 16 | 2026-07-06 | 2026-07-17 |  |  |  |  | 4 | 8
Min Fei | 2026-07-20 |  |  | FIV | FG12 Template Update | Lifestyle | Yan Ren |  | 4 |  |  |  |  | 8 | 2026-07-27 | 2026-07-31 | [5 empty] | 4
Min Fei | 2026-07-20 |  |  | CQS HM | CQS HM OCR Template Develop | Lifestyle | Harry Huang |  | 12 |  |  |  |  | 12 | 2026-07-27 | 2026-07-31 | [5 empty] | 2
Min Fei | 2026-07-06 |  |  | SPS 2.0 | UI Add Classification & ACC ETA And Update Function | Lifestyle | Cherry Tan |  |  | 24 |  |  |  | 24 | 2026-07-20 | 2026-07-24
Min Fei | 2026-05-18 |  |  | FIV | 15 New OCR Template | Lifestyle | Yan Ren |  |  | 8 | 16 |  | 32 | 56 |  | 2026-08-14 |  |  |  | 2026-08-14
Min Fei | 2026-05-11 |  |  | FIV | BD Forwarder Handling Program Development | Lifestyle | Yan Ren |  |  |  | 16 |  | 48 | 64 | 2026-07-01 | 2026-07-31 |  |  |  | 2026-09-15
Min Fei | 2026-05-11 |  |  | FIV | BD OCR Template Development | Lifestyle | Yan Ren | [5 empty] | 104 | 104 | 2026-07-01 | 2026-07-31 |  |  |  | 2026-09-15
Min Fei | 2026-05-15 |  |  | SPS 2.0 | CPPC_N01_HIST Add Customer Department Description | Lifestyle | Cherry Tan | [6 empty] | 4 | 2026-07-13 | 2026-07-17
Min Fei | 2026-07-13 |  |  | CIV | SG CIV eForm | Lifestyle | Yuki Li | [5 empty] | 120 |  | 2026-10-19 | 2026-11-06 |  |  |  | 2026-11-06
Min Fei | 2026-07-06 |  |  | SPS 2.0 | Issues & Enh. | Lifestyle | Cherry Tan | [6 empty] | 116 | 2026-08-24 | 2026-09-11
Min Fei | 2025-10-20 |  |  | SPS 2.0 | UQL Projection Upload & Update | Lifestyle | Cherry Tan | [5 empty] | 40 | 40
Min Fei | 2026-02-02 |  |  | FIV & CIV | Related Service Check And Upgrade Https | Lifestyle | James Duan | [5 empty] | 24 | 24
Min Fei | 2026-01-12 |  |  | Forwarder Invoice | Setup Pipeline | Lifestyle | Max Chen | [5 empty] | 8 | 8
Min Fei | 2026-01-12 |  |  | Courier Invoice | Setup Pipeline | Lifestyle | Max Chen | [5 empty] | 8 | 8
Min Fei | 2025-12-15 |  |  | RPA | Playwright Q2 | Lifestyle | James Duan | [6 empty] | 96 | 2026-05-04 | 2026-07-03 |  |  |  |  | 32
Min Fei |  |  |  | Fastpath | Fastpath | LifeStyle |  |  | 8 | 8 | 8 | 8
[9 empty] | 40 | 40 | 40 | 8 | 384 | 654 | [7 empty] | 40

## Plan_01-03
系统 | 开发事项 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期 | 记录日期
|  | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26
|  | 2026-06-19 | 2026-06-26 | 2026-07-03 | 2026-07-10 | 2026-07-17 | 2026-07-24 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-28 | 2026-09-04 | 2026-09-11 | 2026-09-18 | 2026-09-25 | 2026-10-02 | 2026-10-09 | 2026-10-16 | 2026-10-23 | 2026-10-30
Holiday | 端午 | 2026-06-19: 8
Playwright | Playwright Q2 | 2026-06-26: 8; 2026-07-03: 16; 2026-07-10: 16; 2026-07-17: 16; 2026-07-24: 8
Group eForm | Fixed Assets PO Issues | 2026-06-19: 24
Sales Plan | Enh. | 2026-06-26: 16; 2026-07-03: 16; 2026-07-10: 16
AR Settlement Clearing | MS & H&M Enh. | 2026-06-26: 8
FIV | 15 New OCR Template | 2026-07-17: 16; 2026-07-24: 16; 2026-07-31: 16; 2026-08-07: 8
FIV | BD Forwarder Handling Program Development | 2026-07-24: 8; 2026-07-31: 16; 2026-08-07: 16
FIV | BD OCR Template Development | 2026-08-07: 8; 2026-08-14: 16; 2026-08-21: 16; 2026-08-28: 16; 2026-09-04: 16
SPS2.0 | Issues & Enh. | 2026-08-14: 16; 2026-08-21: 16; 2026-08-28: 16
Fastpath | Fastpath | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
|  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 24

## Completed - 2024
Developer | Report Date | Project ID | CHARM No. | Program Title | Program Description | Initiated Company (Denim, CKL, Sweater, Intimate, T-Shirt, T-Shirt & Sweater) | Requested By | Advised By | This Week | Next Week 1 | Next Week 2 | Next Week 3 | Over 4 Week | Total Man Hrs per Program | Plan Start Date | Plan Completion Date | Revised Start Date | Revised COM Date | No. of times on Revise COM Date | User request Completion Date | Last Week Cumulated Man Hrs | Weekly allocated Man Hrs | Allocated Man Hrs | Actual COM Date | Remark | Functional Team Expected Development Date | Outsource | Priority | F/S ready date | F/S URL | F/S Confirm or Not? | F/S Confirm Date
Min Fei | 2024-10-07 |  |  | Holiday | 国庆节 | LifeStyle | [15 empty] | 24 | 24 | 2024-10-03
Min Fei | 2024-10-07 |  |  | CA 2.0 | Hardcopy | LifeStyle | Bin Wu | [6 empty] | 8 | 2024-10-07 | 2024-10-11 | [5 empty] | 8 | 8 | 2024-10-11
Min Fei | 2024-10-07 |  |  | AR Settelement | Handover | LifeStyle | Max Chen | [6 empty] | 8 | 2024-10-07 | 2024-10-11 | [5 empty] | 8 | 8 | 2024-10-11
Min Fei | 2024-10-07 |  |  | Fastpath | Study FIV & CIV Logic | LifeStyle | [7 empty] | 8 | 2024-10-07 | 2024-10-11 | [5 empty] | 8 | 8 | 2024-10-11
Min Fei | 2024-10-14 |  |  | Fastpath | Fastpath - FIV & CIV Problem | LifeStyle | Yuki Li | [6 empty] | 8 | 2024-10-14 | 2024-10-18 | [5 empty] | 8 | 8 | 2024-10-18
Min Fei | 2024-12-02 |  |  | Holiday | 病假 | LifeStyle | [15 empty] | 8 | 8 | 2024-11-25
Min Fei | 2024-12-02 |  |  | ARSC | new customer OCR template develop | LifeStyle | Max Chen | [6 empty] | 16 | 2024-11-25 | 2024-11-30 | [5 empty] | 16 | 16 | 2024-11-30
Min Fei | 2024-12-02 |  |  | FIV | vendor name update and test | LifeStyle | Yan Ren | [6 empty] | 16 | 2024-11-25 | 2024-11-30 | [5 empty] | 16 | 16 | 2024-11-30
Min Fei | 2024-12-02 |  |  | FIV | Issue | LifeStyle | Yan Ren | [6 empty] | 16 | 2024-12-02 | 2024-11-06 | [5 empty] | 16 | 16 | 2024-12-06
Min Fei | 2024-12-02 |  |  | OCR | FlexiCapture Study | LifeStyle | [7 empty] | 8 | 2024-12-02 | 2024-11-06 | [5 empty] | 8 | 8 | 2024-12-06
Min Fei | 2024-12-09 |  |  | FastPath | Fast-OCR Template And FIV Problem | LifeStyle | Yan Ren | [6 empty] | 16 | 2024-12-02 | 2024-11-06 | [5 empty] | 16 | 16 | 2024-12-06
Min Fei | 2024-12-02 |  |  | ARSC | Pahse 2 Issue | LifeStyle | Yuki Li | [6 empty] | 8 | 2024-12-02 | 2024-12-06 | 2024-12-09 | 2024-12-13 | 1 |  |  | 8 | 8 | 2024-12-13
Min Fei | 2024-12-02 |  |  | ARSC | Fastpath - FG15 OCR Template Update | LifeStyle | Yan Ren | [6 empty] | 8 | 2024-12-09 | 2024-12-13 | [5 empty] | 8 | 8 | 2024-12-13
Min Fei | 2024-12-02 |  |  | FIV | FG16 Vendor Name PRD Mapping Problem | LifeStyle | Yan Ren | [6 empty] | 8 | 2024-12-09 | 2024-12-13 | [5 empty] | 8 | 8 | 2024-12-13
Min Fei | 2024-12-02 |  |  | ARSC | Mail Rule Or Program Move Mail | LifeStyle | Yuki Li | [6 empty] | 8 | 2024-12-09 | 2024-12-13 | 2024-12-16 | 2024-12-20 | 1 |  |  | 8 | 8 | 2024-12-20
Min Fei | 2024-12-02 |  |  | ARSC | Pahse 1 Customer Ehn. | LifeStyle | Max Chen | [6 empty] | 24 | 2024-12-09 | 2024-12-20 |  |  |  |  | 16 | 8 | 24 | 2024-12-20
Min Fei | 2024-12-23 |  |  | FIV | Fastpath-FG16 Invoice Date Handle | LifeStyle | Yan Ren | [6 empty] | 8 | 2024-12-16 | 2024-12-20 | [5 empty] | 8 | 8 | 2024-12-20
Min Fei | 2024-12-23 |  |  | Holiday | 病假 | LifeStyle | [7 empty] | 8 | [7 empty] | 8 | 8
Min Fei | 2024-12-02 |  |  | ORSO | Study | LifeStyle | Bin Wu | [6 empty] | 24 | 2024-12-16 | 2024-12-27 |  | 2024-12-27 | 1 |  | 8 | 16 | 24 | 2024-12-27
Min Fei | 2024-12-30 |  |  | Fastpath | FIV - FG16 Invoice No unable to display | LifeStyle | Yan Ren | [6 empty] | 8 | 2024-12-23 | 2024-12-27 | [5 empty] | 8 | 8 | 2024-12-27
Min Fei | 2024-12-02 |  |  | Sales Plan | Study | LifeStyle | Bin Wu | [6 empty] | 32 | 2024-12-23 | 2025-01-03 |  | 2025-01-03 | 1 |  | 16 | 16 | 32 | 2025-01-03

## Completed - 2025
Developer | Report Date | Project ID | CHARM No. | Program Title | Program Description | Initiated Company (Denim, CKL, Sweater, Intimate, T-Shirt, T-Shirt & Sweater) | Requested By | Advised By | This Week | Next Week 1 | Next Week 2 | Next Week 3 | Over 4 Week | Total Man Hrs per Program | Plan Start Date | Plan Completion Date | Revised Start Date | Revised COM Date | No. of times on Revise COM Date | User request Completion Date | Last Week Cumulated Man Hrs | Weekly allocated Man Hrs | Allocated Man Hrs | Actual COM Date | Remark | Functional Team Expected Development Date | Outsource | Priority | F/S ready date | F/S URL | F/S Confirm or Not? | F/S Confirm Date
Min Fei | 2024-12-02 |  |  | Sales Plan | Study | LifeStyle | Bin Wu | [6 empty] | 32 | 2024-12-23 | 2025-01-03 |  | 2025-01-03 | 1 |  | 16 | 16 | 32 | 2025-01-03
Min Fei | 2024-12-09 |  |  | Holiday | 元旦 | LifeStyle | [7 empty] | 8 | 2024-12-30 | 2025-01-03 | [5 empty] | 8 | 8 | 2025-01-03
Min Fei | 2025-01-06 |  |  | Sales Plan | fixed issues | LifeStyle | Bin Wu | [6 empty] | 16 | 2024-12-30 | 2025-01-03 | [5 empty] | 16 | 16 | 2025-01-03
Min Fei | 2024-12-09 |  |  | OCR | OCR Web Service Study | LifeStyle | Max Chen | [6 empty] | 16 | 2024-12-30 | 2025-01-03 | 2025-01-06 | 2025-01-10 | 1 |  |  | 16 | 16 | 2025-01-10
Min Fei | 2025-01-13 |  |  | Fastpath-FIV | Create FG51 Template | LifeStyle | Yan Ren | [6 empty] | 4 | 2025-01-06 | 2025-01-10 | [5 empty] | 4 | 4 | 2025-01-10
Min Fei | 2025-01-13 |  |  | Fastpath-SOH | Create FNB1 Template | LifeStyle | Happy Liu | [6 empty] | 4 | 2025-01-06 | 2025-01-10 | [5 empty] | 4 | 4 | 2025-01-10
Min Fei | 2025-01-13 |  |  | Sales Plan | Fixed issues | LifeStyle | Jassie Zhou | [6 empty] | 16 | 2025-01-06 | 2025-01-10 | [5 empty] | 16 | 16 | 2025-01-10
Min Fei | 2025-01-20 |  |  | ARSC | ARSC PRD Release Fixed Issues | LifeStyle | Yuki | [6 empty] | 24 | 2025-01-13 | 2020-01-17 | [5 empty] | 24 | 24 | 2025-01-17
Min Fei | 2025-01-13 |  |  | Sales Plan | Require complate issues before year | LifeStyle | Jassie Zhou | [6 empty] | 32 | 2025-01-13 | 2025-01-24 |  |  |  |  | 16 | 16 | 32 | 2025-01-24
Min Fei | 2025-01-20 |  |  | SOH | HMSampleOrder Study | LifeStyle | Max Chen | [6 empty] | 8 | 2025-01-20 | 2025-01-24 | [5 empty] | 8 | 8 | 2025-01-24
Min Fei | 2025-01-20 |  |  | Sales Plan | Fixed Warning | LifeStyle | Max Chen | [6 empty] | 4 | 2025-01-20 | 2025-01-24 | [5 empty] | 4 | 4 | 2025-01-24
Min Fei | 2025-01-20 |  |  | CIV | Fixed Warning | LifeStyle | Max Chen | [6 empty] | 4 | 2025-01-20 | 2025-01-24 | [5 empty] | 4 | 4 | 2025-01-24
Min Fei | 2025-01-06 |  |  | Holiday | 春节 | LifeStyle | [7 empty] | 64 | 2025-01-27 | 2025-02-05 | [5 empty] | 64 | 64 | 2025-02-05
Min Fei | 2025-02-10 |  |  | ARSC | ARSC PRD Problems | LifeStyle | Yuki Li | [6 empty] | 8 | 2025-02-03 | 2025-02-07 | [5 empty] | 8 | 8 | 2025-02-07
Min Fei | 2025-02-10 |  |  | FIV | FG49 OCR Problem | LifeStyle | Yan Ren | [6 empty] | 4 | 2025-02-03 | 2025-02-07 | [5 empty] | 4 | 4 | 2025-02-07
Min Fei | 2025-02-24 |  |  | FIV | FG23 Template compatible with new styles | LifeStyle | Yuki Li | [6 empty] | 5 | 2025-02-17 | 2025-02-21 | [5 empty] | 5 | 5 | 2025-02-21
Min Fei | 2025-02-24 |  |  | FIV | Intimate FIV system run problem | LifeStyle | Yuki Li | [6 empty] | 3 | 2025-02-17 | 2025-02-21 | [5 empty] | 3 | 3 | 2025-02-21
Min Fei | 2025-03-03 |  |  | Holiday | 请假 | LifeStyle | [7 empty] | 3.5 | 2025-02-24 | 2025-02-28 | [5 empty] | 3.5 | 4 | 2025-02-28
Min Fei | 2025-01-20 |  |  | ORSO | Issues | LifeStyle | Jennifer Lee | [6 empty] | 64 | 2025-02-10 | 2025-02-21 |  | 2025-02-28 | 1 |  | 56 | 16 | 72 | 2025-02-28
Min Fei | 2025-03-03 |  |  | ORSO | Fastpath - ORSO test and test report | LifeStyle | Jennifer Lee | [6 empty] | 12 | 2025-02-24 | 2025-02-28 | [5 empty] | 12 | 12 | 2025-02-28
Min Fei | 2025-03-03 |  |  | VapQuotation | VAP Quotation Study | Lifestyle | Jenny Chen | [6 empty] | 16 | 2025-03-03 | 2025-03-07 | [5 empty] | 16 | 16 | 2025-03-07
Min Fei | 2025-03-10 |  |  | ORSO | ORSO Optimization and Testing | Lifestyle | Jennifer Lee | [6 empty] | 12 | 2025-03-03 | 2025-03-07 | [5 empty] | 12 | 12 | 2025-03-07
Min Fei | 2025-03-10 |  |  | FIV | Fixed Add Assignment | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-03-03 | 2025-03-07 | [5 empty] | 4 | 4 | 2025-03-07
Min Fei | 2025-03-17 |  |  | FIV | FG15、FG17 OCR Template Update | Lifestyle | Yan Ren | [6 empty] | 6 | 2025-03-10 | 2025-03-14 | [5 empty] | 6 | 6 | 2025-03-14
Min Fei | 2025-03-17 |  |  | CIV | CIV Cannot match in EMS Problem | Lifestyle | Yuki Li | [6 empty] | 2 | 2025-03-10 | 2025-03-14 | [5 empty] | 2 | 2 | 2025-03-14
Min Fei | 2025-02-10 |  |  | Sales Plan | Fixed UAT Issues(priority) | LifeStyle | Jassie Zhou | [6 empty] | 40 | 2025-02-06 | 2025-02-28 |  |  |  |  | 32 | 8 | 40 | 2025-03-14
Min Fei | 2025-03-10 |  |  | VapQuotation | VAP Quotation Fixed Issues | Lifestyle | Jenny Chen | [6 empty] | 20 | 2025-03-10 | 2025-03-14 | [5 empty] | 20 | 20 | 2025-03-14
Min Fei | 2025-03-10 |  |  | ARSC | ARSC ​Requirements Alignment | Lifestyle | Lynn Wang | [6 empty] | 4 | 2025-03-10 | 2025-03-14 | [5 empty] | 4 | 4 | 2025-03-14
Min Fei | 2025-03-24 |  |  | FIV | FG17 OCR Error and Template Update | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-03-17 | 2025-03-21 | [5 empty] | 4 | 4 | 2025-03-21
Min Fei | 2025-03-24 |  |  | VapQuotation | stored procedure update and Fixed Bug | Lifestyle | Jenny Chen | [6 empty] | 12 | 2025-03-17 | 2025-03-21 | [5 empty] | 12 | 12 | 2025-03-21
Min Fei | 2025-03-17 |  |  | Sales Plan | Fixed Issues | Lifestyle | Jassie Zhou | [6 empty] | 40 | 2025-03-17 | 2025-03-28 |  |  |  |  | 24 | 16 | 40 | 2025-03-28
Min Fei | 2025-03-31 |  |  | Courier Invoice | FOB01 Template Update | Lifestyle | Yuki Li | [6 empty] | 3 | 2025-03-24 | 2025-03-28 | [5 empty] | 3 | 3 | 2025-03-28
Min Fei | 2025-03-31 |  |  | Forwarder Invoice | FG16 Template Update | Lifestyle | Yan Ren | [6 empty] | 3 | 2025-03-24 | 2025-03-28 | [5 empty] | 3 | 3 | 2025-03-28
Min Fei | 2025-03-31 |  |  | Forwarder Invoice | FG17 Template Update | Lifestyle | Yan Ren | [6 empty] | 2 | 2025-03-24 | 2025-03-28 | [5 empty] | 2 | 2 | 2025-03-28
Min Fei | 2025-03-24 |  |  | Sales Plan | Fixed Warning SCS0027 | Lifestyle | Max Chen | [6 empty] | 4 | 2025-03-24 | 2025-03-28 | [5 empty] | 4 | 4 | 2025-03-28
Min Fei | 2025-03-24 |  |  | VapQuotation | Fixed Internal Report | Lifestyle | Jenny Chen | [6 empty] | 4 | 2025-03-24 | 2025-03-28 | [5 empty] | 4 | 4 | 2025-03-28
Min Fei | 2025-03-17 |  |  | Sales Plan | Fixed Issues - Add Hardcopy | Lifestyle | Jassie Zhou | [6 empty] | 24 | 2025-03-24 | 2025-04-04 |  |  |  |  | 8 | 24 | 32 | 2025-04-04
Min Fei | 2025-03-10 |  |  | Holiday | 清明 | Lifestyle | [7 empty] | 8 | 2025-03-31 | 2025-04-04 | [5 empty] | 8 | 8 | 2025-04-04
Min Fei | 2025-04-07 |  |  | Fastpath | FG17 OCR Template Update | Lifestyle | Yan Ren | [6 empty] | 2 | 2025-03-31 | 2025-04-04 | [5 empty] | 2 | 2 | 2025-04-04
Min Fei | 2025-04-07 |  |  | Fastpath | FG25 OCR Template Update | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-03-31 | 2025-04-04 | [5 empty] | 4 | 4 | 2025-04-04
Min Fei | 2025-04-07 |  |  | Fastpath | EDIQAS Email Account Locked | Lifestyle | [7 empty] | 2 | 2025-03-31 | 2025-04-04 | [5 empty] | 2 | 2 | 2025-04-04
Min Fei | 2025-04-14 |  |  | Forwarder Invoice | Web Job Invalidaty Problem | LifeStyle | Yuki Li | [6 empty] | 2 | 2025-04-07 | 2025-04-11 | [5 empty] | 2 | 2 | 2025-04-11
Min Fei | 2025-04-14 |  |  | Forwarder Invoice | Web Access Slow Problem | LifeStyle | Yan Ren | [6 empty] | 4 | 2025-04-07 | 2025-04-11 | [5 empty] | 4 | 4 | 2025-04-11
Min Fei | 2025-04-14 |  |  | Courier Invoice | “HKGIR02694185.pdf ”No Match And Remote DB Connect fail | LifeStyle | Yuki Li | [6 empty] | 4 | 2025-04-07 | 2025-04-11 | [5 empty] | 4 | 4 | 2025-04-11
Min Fei | 2025-04-14 |  |  | AR Settlement Clearing | Web Job Invalidaty Problem | LifeStyle | Yuki Li | [6 empty] | 2 | 2025-04-07 | 2025-04-11 | [5 empty] | 2 | 2 | 2025-04-11
Min Fei | 2025-04-14 |  |  | Sales Plan | Optimization Issues | LifeStyle | Jassie Zhou | [6 empty] | 4 | 2025-04-07 | 2025-04-11 | [5 empty] | 4 | 4 | 2025-04-11
Min Fei | 2025-04-21 |  |  | Sales Plan | QAS Test Issues | LifeStyle | Jassie Zhou | [6 empty] | 4 | 2025-04-14 | 2025-04-18 | [5 empty] | 4 | 4 | 2025-04-18
Min Fei | 2025-04-21 |  |  | Sales Plan | QAS Login Error | LifeStyle | Jassie Zhou | [6 empty] | 4 | 2025-04-14 | 2025-04-18 | [5 empty] | 4 | 4 | 2025-04-18
Min Fei | 2025-04-28 |  |  | Forwarder Invoice | FG49 Identification Error | LifeStyle | Yan Ren | [6 empty] | 3 | 2025-04-21 | 2025-04-25 | [5 empty] | 3 | 3 | 2025-04-25
Min Fei | 2025-04-28 |  |  | Forwarder Invoice | FG25 Template Change Error | LifeStyle | Yan Ren | [6 empty] | 3 | 2025-04-21 | 2025-04-25 | [5 empty] | 3 | 3 | 2025-04-25
Min Fei | 2025-04-28 |  |  | Sales Plan | fixed UAT Issues | LifeStyle | Jassie Zhou | [6 empty] | 2 | 2025-04-21 | 2025-04-25 | [5 empty] | 2 | 2 | 2025-04-25
Min Fei | 2025-04-14 |  |  | Holiday | 五一 | LifeStyle | [7 empty] | 16 | 2025-04-28 | 2025-05-02 | [5 empty] | 16 | 16 | 2025-05-02
Min Fei | 2025-05-05 |  |  | VapQuotation | PRD Deployment | LifeStyle | Jenny Chen | [6 empty] | 4 | 2025-04-28 | 2025-05-02 | [5 empty] | 4 | 4 | 2025-05-02
Min Fei | 2025-05-05 |  |  | VapQuotation | fixed Data Display Error & update EF Structure | LifeStyle | Jenny Chen | [6 empty] | 12 | 2025-04-28 | 2025-05-02 | [5 empty] | 12 | 12 | 2025-05-02
Min Fei | 2025-05-05 |  |  | Forwarder Invoice | FG25 Multiple Pages Problem | LifeStyle | Yan Ren | [6 empty] | 4 | 2025-04-28 | 2025-05-02 | [5 empty] | 4 | 4 | 2025-05-02
Min Fei | 2025-05-05 |  |  | Sales Plan | Fixed Bug | LifeStyle | Jassie Zhou | [6 empty] | 4 | 2025-04-28 | 2025-05-02 | [5 empty] | 4 | 4 | 2025-05-02
Min Fei | 2025-05-12 |  |  | Fastpath | Sales Plan Optimization Issues | LifeStyle | Jassie Zhou | [6 empty] | 6 | 2025-05-05 | 2025-05-09 | [5 empty] | 6 | 6 | 2025-05-09
Min Fei | 2025-05-12 |  |  | Fastpath | Sales Plan QAS & VAPQuotation Mapping Maintenance | LifeStyle | Jassie&Jenny | [6 empty] | 1 | 2025-05-05 | 2025-05-09 | [5 empty] | 1 | 1 | 2025-05-09
Min Fei | 2025-05-12 |  |  | Fastpath | ARSC PRD Problem | LifeStyle | Yuki Li | [6 empty] | 1 | 2025-05-05 | 2025-05-09 | [5 empty] | 1 | 1 | 2025-05-09
Min Fei | 2025-03-31 |  |  | AR Settlement Clearing | Phase 3 | Lifestyle | Lynn Wang | [6 empty] | 144 | 2025-04-07 | 2025-05-09 |  | 2025-05-16 | 1 |  | 120 | 24 | 144 | 2025-05-16
Min Fei | 2025-05-19 |  |  | Fastpath | Sales Plan Fixed Bug | Lifestyle | Jassie Zhou | [6 empty] | 6 | 2025-05-12 | 2025-05-16 | [5 empty] | 6 | 6 | 2025-05-16
Min Fei | 2025-05-19 |  |  | Fastpath | Forwarder Invoice FG51 Problem | Lifestyle | Yan Ren | [6 empty] | 2 | 2025-05-12 | 2025-05-16 | [5 empty] | 2 | 2 | 2025-05-16
Min Fei | 2025-03-31 |  |  | AR Settlement Clearing | Optimization Issues | Lifestyle | Lynn Wang | [6 empty] | 16 | 2025-05-05 | 2025-05-09 | 2025-05-12 | 2025-05-23 | 1 |  | 8 | 12 | 20 | 2025-05-23
Min Fei | 2025-05-12 |  |  | AR Settlement Clearing | Phase 2 Optimization Issues | LifeStyle | Yuki Li | [6 empty] | 24 | 2025-05-19 | 2025-05-23 | [5 empty] | 24 | 24 | 2025-05-23
Min Fei | 2025-05-26 |  |  | Sales Plan | QAS Budget Error Add Log | Lifestyle | Jassie Zhou | [6 empty] | 4 | 2025-05-19 | 2025-05-23 | [5 empty] | 4 | 4 | 2025-05-23
Min Fei | 2025-05-26 |  |  | CIV、Sales Plan | Fixed DI Error Test | Lifestyle | Max Chen | [6 empty] | 8 | 2025-05-26 | 2025-05-30 | [5 empty] | 8 | 8 | 2025-05-30
Min Fei | 2025-05-26 |  |  | Forwarder Invoice | Fixed DI Error | Lifestyle | Max Chen | [6 empty] | 8 | 2025-05-26 | 2025-05-30 | [5 empty] | 8 | 8 | 2025-05-30
Min Fei | 2025-05-26 |  |  | AR Settlement Clearing | Phase 3 Test & Fixed Bug | LIfestyle | Lynn Wang | [6 empty] | 16 | 2025-05-26 | 2025-05-30 | [5 empty] | 12 | 12 | 2025-05-30
Min Fei | 2025-06-03 |  |  | AR Settlement Clearing | Phase 2 Optimization Test | Lifestyle | Yuki Li | [6 empty] | 6 | 2025-05-26 | 2025-05-30 | [5 empty] | 6 | 6 | 2025-05-30
Min Fei | 2025-06-03 |  |  | Forwarder Invoice | FG15 Template VendorName Identification Error | Lifestyle | Yan Ren | [6 empty] | 2 | 2025-05-26 | 2025-05-30 | [5 empty] | 2 | 2 | 2025-05-30
Min Fei | 2025-06-03 |  |  | CIV & FIV | Knits & Intimate Permission Update | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-05-26 | 2025-05-30 | [5 empty] | 4 | 4 | 2025-05-30
Min Fei | 2025-06-09 |  |  | Forwarder Invoice | FG24 Template and Mapping Update & Scc Config Update | Lifestyle | Yan Ren | [6 empty] | 8 | 2025-06-02 | 2025-06-06 | [5 empty] | 8 | 8 | 2025-06-06
Min Fei | 2025-06-09 |  |  | Sales Plan | Fixed Issues | Lifestyle | Jassie Zhou | [6 empty] | 8 | 2025-06-02 | 2025-06-06 | [5 empty] | 8 | 8 | 2025-06-06
Min Fei | 2025-06-09 |  |  | Sales Plan | QAS Deployment | Lifestyle | Jassie Zhou | [6 empty] | 4 | 2025-06-02 | 2025-06-06 | [5 empty] | 4 | 4 | 2025-06-06
Min Fei | 2025-06-09 |  |  | SOH | PRD Problem | Intimate | JiaJing Wu | [6 empty] | 4 | 2025-06-02 | 2025-06-06 | [5 empty] | 4 | 4 | 25--6-6
Min Fei | 2025-05-12 |  |  | Holiday | 端午 | LifeStyle | [7 empty] | 8 | 2025-06-02 | 2025-06-06 | [5 empty] | 8 | 8 | 2025-06-06
Min Fei | 2025-06-16 |  |  | Holiday | 请假 | Lifestyle | [7 empty] | 4 | 2025-06-09 | 2025-06-13 | [5 empty] | 4 | 4 | 2025-06-13
Min Fei | 2025-06-16 |  |  | AR Settlement Clearing | QAS Environment Deploy Cannot find package | Lifestyle | Yuki Li | [6 empty] | 4 | 2025-06-09 | 2025-06-13 | [5 empty] | 4 | 4 | 2025-06-13
Min Fei | 2025-06-16 |  |  | AR Settlement Clearing | Phase2&3 QAS Environment Release And Test | Lifestyle | Yuki Li | [6 empty] | 4 | 2025-06-09 | 2025-06-13 | [5 empty] | 4 | 4 | 2025-06-13
Min Fei | 2025-06-09 |  |  | Forwarder Invoice | FG52 New Template Development | Lifestyle | YanRen | [6 empty] | 16 | 2025-06-09 | 2025-06-13 | [5 empty] | 16 | 16 | 2025-06-13
Min Fei | 2025-06-16 |  |  | Forwarder Invoice | New Version Program Release And Test | Lifestyle | YanRen | [6 empty] | 2 | 2025-06-09 | 2025-06-13 | [5 empty] | 2 | 2 | 2025-06-13
Min Fei | 2025-06-23 |  |  | AR Settlement Clearing | Phase3 QAS with Test | Lifestyle | Yuki Li & Lynn Wang | [6 empty] | 12 | 2025-06-16 | 2025-06-20 | [5 empty] | 12 | 12 | 2025-06-20
Min Fei | 2025-06-16 |  |  | SOH-H&M | OCR Template Update | Intimate | JiaJing Wu | [6 empty] | 16 | 2025-06-09 | 2025-06-20 |  |  |  |  | 8 | 8 | 16 | 2025-06-20
Min Fei | 2025-06-09 |  |  |  | Adidas Ocr Template Update | Lifestyle | James Duan | [6 empty] | 8 | 2025-06-16 | 2025-06-20 | 2025-06-23 | 2025-06-27 | 1 |  |  | 8 | 8 | 2025-06-27
Min Fei | 2025-06-30 |  |  | SOH-H&M | QAS Environment Problem | Lifestyle | JiaJing Wu | [6 empty] | 8 | 2025-06-23 | 2025-06-27 | [5 empty] | 8 | 8 | 2025-06-27
Min Fei | 2025-06-23 |  |  | AR Settlement Clearing | Phase3 Fixed Issues | Lifestyle | Lynn Wang | [6 empty] | 8 | 2025-06-23 | 2025-06-27 |  | 2025-07-04 | 1 |  |  | 8 | 8 | 2025-07-04
Min Fei | 2025-07-07 |  |  | SOH-H&M | FNB2 OCR Template Update | Lifestyle | JiaJing Wu | [6 empty] | 8 | 2025-06-30 | 2025-07-04 | [5 empty] | 8 | 8 | 2025-07-04
Min Fei | 2025-06-30 |  |  | Forwarder Invoice | FG04、FG05、FG11 Template Update | Lifestyle | Yan Ren | [6 empty] | 16 | 2025-06-30 | 2025-07-11 | [5 empty] | 8 | 8 | 2025-07-04
Min Fei | 2025-06-16 |  |  | SOH-H&M | Process OCR Result Program Update | Intimate | JiaJing Wu | [6 empty] | 8 | 2025-06-16 | 2025-06-20 |  | 2025-07-04 | 1 |  | 12 | 4 | 16 | 2025-07-04
Min Fei | 2025-07-07 |  |  | AR Settlement Clearing | Phase2 Fixed Issues | Lifestyle | Yuki Li | [6 empty] | 4 | 2025-07-07 | 2025-07-11 | [5 empty] | 4 | 4 | 2025-07-11
Min Fei | 2025-07-07 |  |  | AR Settlement Clearing | Phase3 PRD Release | Lifestyle | Lynn Wang | [6 empty] | 4 | 2025-07-07 | 2025-07-11 | [5 empty] | 4 | 4 | 2025-07-11
Min Fei | 2025-06-09 |  |  | Sales Plan | Fixed Issues & Enh | Lifestyle | Jassie Zhou | [6 empty] | 40 | 2025-06-09 | 2025-07-04 |  | 2025-07-11 | 1 |  | 24 | 16 | 40 | 2025-07-11
Min Fei | 2025-06-30 |  |  | Forwarder Invoice | FG53 New Template Develop | Lifestyle | Yan Ren | [6 empty] | 8 | 2025-07-07 | 2025-07-11 | [5 empty] | 8 | 8 | 2025-07-11
Min Fei | 2025-07-07 |  |  | Forwarder Invoice | Performance Problem Check | Lifestyle | Yan Ren | [6 empty] | 16 | 2025-06-30 | 2025-07-11 |  |  |  |  | 8 | 8 | 16 | 2025-07-11
Min Fei | 2025-07-14 |  |  | SOH-H&M | FNB2 Template Update and TimeOfDelivery Special Handling | Intimate | JiaJing Wu | [6 empty] | 8 | 2025-07-14 | 2025-07-18 | [5 empty] | 12 | 12 | 2025-07-18
Min Fei | 2025-07-14 |  |  | AR Settlement Clearing | Optimization | Lifestyle | Yuki Li | [6 empty] | 16 | 2025-07-21 | 2025-07-25 | 2025-07-14 | 2025-07-18 | 1 |  |  | 16 | 16 | 2025-07-18
Min Fei | 2025-07-21 |  |  | Forwarder Invoice | Housekeeping Study and Update | Lifestyle | James Duan | [6 empty] | 4 | 2025-07-14 | 2025-07-18 | [5 empty] | 4 | 4 | 2025-07-18
Min Fei | 2025-07-21 |  |  | Fastpath | Sales Plan Problem Check | Lifestyle | Jassie Zhou | [6 empty] | 4 | 2025-07-14 | 2025-07-18 | [5 empty] | 4 | 4 | 2025-07-18
Min Fei | 2021-07-25 |  |  | Fastpath | AR Settlement Clearing Problem Check | Lifestyle | Yuki Li | [6 empty] | 4 | 2025-07-14 | 2025-07-18 | [5 empty] | 4 | 4 | 2025-07-18
Min Fei | 2025-07-14 |  |  | Forwarder Invoice | FG25 Template Update | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-07-14 | 2025-07-18 | 2025-07-21 | 2025-07-25 | 1 |  |  | 4 | 4 | 2025-07-25
Min Fei | 2025-07-21 |  |  | Forwarder Invoice | FG15 Template Recognition Error | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-07-21 | 2025-07-25 | [5 empty] | 6 | 6 | 2025-07-25
Min Fei | 2025-07-28 |  |  | Forwarder Invoice | FG02 Error Check | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-07-21 | 2025-07-25 | [5 empty] | 4 | 4 | 2025-07-25
Min Fei | 2025-07-21 |  |  | SOH-H&M | PurchaseOrder PDF Color Overlength Problem | Intimate | JiaJing Wu | [6 empty] | 8 | 2025-07-21 | 2025-07-25 | [5 empty] | 12 | 12 | 2025-07-25
Min Fei | 2025-07-21 |  |  |  | Adidas OCR Template Update | Lifestyle | Cindy Mo | [6 empty] | 6 | 2025-07-21 | 2025-07-25 |  | 2025-08-01 | 1 |  | 6 | 4 | 10 | 2025-08-01
Min Fei | 2025-07-21 |  |  | Forwarder Invoice | Nlog Optimization | Lifestyle | James Duan | [6 empty] | 8 | 2025-07-28 | 2025-08-01 | [5 empty] | 8 | 8 | 2025-08-01
Min Fei | 2025-08-04 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 5 | 2025-07-28 | 2025-08-01 | [5 empty] | 5 | 5 | 2025-08-01
Min Fei | 2025-08-04 |  |  | Forwarder Invoice | FG16 Template Update | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-07-28 | 2025-08-01 |  |  |  |  | 4 | 4 | 4 | 2025-08-01
Min Fei | 2025-08-04 |  |  | Courier Invoice | Total Amount 0 Check & OCR Template Update | Lifestyle | Harry Huang | [6 empty] | 4 | 2025-07-28 | 2025-08-01 | [5 empty] | 4 | 4 | 2025-08-01
Min Fei | 2025-07-28 |  |  | SOH-H&M | FNB2 Program Overwrite | Intimate | JiaJing Wu | [6 empty] | 40 | 2025-07-28 | 2025-08-08 |  |  |  |  | 8 | 32 | 40 | 2025-08-08
Min Fei | 2025-08-11 |  |  | Meeting | Meeting | LifeStyle | [7 empty] | 5 | 2025-08-04 | 2025-08-08 |  |  |  |  | 5 | 5 | 5 | 2025-08-08
Min Fei | 2025-08-18 |  |  | SOH-H&M | Program Enh. | Intimate | JiaJing Wu | [6 empty] | 8 | 2025-08-11 | 2025-08-15 |  |  |  |  | 8 | 8 | 8 | 2025-08-15
Min Fei | 2025-02-24 |  |  | SPS 2.0 | Study | LifeStyle | Max Chen | [6 empty] | 24 | 2025-06-09 | 2025-06-13 | [5 empty] | 24 | 24 | 2025-08-15
Min Fei | 2025-07-21 |  |  | Sales Plan | Sales Plan Fixed Issues And Support | Lifestyle | Jassie Zhou | [6 empty] | 16 | 2025-07-21 | 2025-08-01 |  | 2025-08-22 | 1 |  | 27 | 8 | 35 | 2025-08-22
Min Fei | 2025-08-11 |  |  | Sales Plan | Sales Plan Test Report | LifeStyle | James Duan | [6 empty] | 8 | 2025-08-18 | 2025-08-22 | [5 empty] | 8 | 8 | 2025-08-22
Min Fei | 2025-08-04 |  |  | Mail Tools | Mail Tools Enh. | Lifestyle | James Duan | [6 empty] | 8 | 2025-08-18 | 2025-08-22 | [5 empty] | 16 | 16 | 2025-08-22
Min Fei | 2025-08-25 |  |  | SOH-H&M | TimeOfDeliver Table convert Repeating Group | Intimate | JiaJing Wu | [6 empty] | 4 | 2025-08-18 | 2025-08-22 | [5 empty] | 6 | 6 | 2025-08-22
Min Fei | 2025-07-14 |  |  | ARSC、CIV、Sales Plan | HouseKeeping Study and Setting | Lifestyle | James Duan | [6 empty] | 8 | 2025-08-25 | 2025-08-29 | [5 empty] | 8 | 8 | 2025-08-29
Min Fei | 2025-08-11 |  |  | Forwarder Invoice | Forwarder Invoice Test Report | LifeStyle | James Duan | [6 empty] | 8 | 2025-08-25 | 2025-08-29 | [5 empty] | 8 | 8 | 2025-08-29
Min Fei | 2025-09-01 |  |  | Courier Invoice | Exception Check | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-08-25 | 2025-08-29 | [5 empty] | 4 | 4 | 2025-08-29
Min Fei | 2025-09-01 |  |  | Mail Tools | Requirement and Fixed Bug and Test | Lifestyle | Lynn Wang | [6 empty] | 4 | 2025-08-25 | 2025-08-29 | [5 empty] | 8 | 8 | 2025-08-29
Min Fei | 2025-09-01 |  |  | Sales Plan | Fixed Issues | Lifestyle | Jassie Zhou | [6 empty] | 8 | 2025-09-01 | 2025-09-05 | [5 empty] | 8 | 8 | 2025-09-05
Min Fei | 2025-09-08 |  |  | Courier Invoice | Fixed SapCompleteCallBack API Bug | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-09-01 | 2025-09-05 | [5 empty] | 4 | 4 | 2025-09-05
Min Fei | 2025-09-08 |  |  | Forwarder Invoice | FG25 Template Update | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-09-01 | 2025-09-05 | [5 empty] | 4 | 4 | 2025-09-05
Min Fei | 2025-09-15 |  |  | SOH-H&M | PurchaseOrder and PackingList Data Not Match | Intimate | JiaJing Wu | [6 empty] | 8 | 2025-09-08 | 2025-09-12 | [5 empty] | 8 | 8 | 2025-09-12
Min Fei | 2025-09-08 |  |  | Forwarder Invoice | .NET Framework upgrade 4.8 | Lifestyle | James Duan | [6 empty] | 16 | 2025-09-08 | 2025-09-12 | [5 empty] | 16 | 16 | 2025-09-12
Min Fei | 2025-08-09 |  |  | Forwarder Invoice | FG15 Template Remake | Lifestyle | Yan Ren | [6 empty] | 8 | 2025-09-08 | 2025-09-12 | [5 empty] | 8 | 8 | 2025-09-12
Min Fei | 2025-09-15 |  |  | Courier Invoice | .NET Framework upgrade 4.8 | Lifestyle | Max Chen | [6 empty] | 8 | 2025-09-15 | 2025-09-19 | [5 empty] | 8 | 8 | 2025-09-19
Min Fei | 2025-09-22 |  |  | YEPA | YEPA | Lifestyle | James Duan | [6 empty] | 6 | 2025-09-15 | 2025-09-19 | [5 empty] | 6 | 6 | 2025-09-19
Min Fei | 2025-09-22 |  |  | Sales Plan | TSK DataBase Cleaning | Lifestyle | Jassie Zhou | [6 empty] | 2 | 2025-09-15 | 2025-09-19 | [5 empty] | 2 | 2 | 2025-09-19
Min Fei | 2025-09-29 |  |  | Leave | 台风停工 | Lifestyle | [7 empty] | 8 | 2025-09-22 | 2025-09-26 | [5 empty] | 8 | 8 | 2025-09-26
Min Fei | 2025-08-18 |  |  | SPS 2.0 | Fixed Issues | LifeStyle | Cherry Tan | [6 empty] | 52 | 2025-08-18 | 2025-08-22 |  | 2025-09-26 | 1 |  | 52 | 8 | 60 | 2025-09-26
Min Fei | 2025-09-15 |  |  | AR Settlement Clearing | Phase2 Requirement | Lifestyle | Yuki Li | [6 empty] | 16 | 2025-09-22 | 2025-09-26 | [5 empty] | 16 | 16 | 2025-09-26
Min Fei | 2025-09-29 |  |  | Forwarder Invoice | Vendor Name Mapping Table Update | Lifestyle | Yan Ren | [6 empty] | 2 | 2025-09-22 | 2025-09-26 | [5 empty] | 2 | 2 | 2025-09-26
Min Fei | 2025-09-29 |  |  | Mail Tools | Mail Tools Enh. Release And Test | Lifestyle | Lynn Wang | [6 empty] | 2 | 2025-09-22 | 2025-09-26 | [5 empty] | 2 | 2 | 2025-09-26
Min Fei | 2025-06-16 |  |  | ARSC、FIV、CIV、VapQuotation、ORSO、SalesPlan | MD Docs Document Migrate Wiki | Lifestyle | James Duan | [6 empty] | 16 | 2025-06-30 | 2025-07-04 | 2025-09-22 | 2025-10-03 | 1 |  | 8 | 8 | 16 | 2025-10-03
Min Fei | 2025-09-15 |  |  | Holiday | 国庆节 | Lifestyle | [7 empty] | 24 | 2025-09-29 | 2025-10-03 | [5 empty] | 24 | 24 | 2025-10-03
Min Fei | 2025-09-22 |  |  | Sales Plan | Fixed Issues | Lifestyle | Jassie Zhou | [6 empty] | 8 | 2025-09-29 | 2025-10-03 | [5 empty] | 8 | 8 | 2025-10-03
Min Fei | 2025-09-15 |  |  | Holiday | 中秋节 | Lifestyle | [7 empty] | 8 | 2025-10-06 | 2025-10-10 | [5 empty] | 8 | 8 | 2025-10-10
Min Fei | 2025-10-07 |  |  | SPS 2.0 | Upload Projection Requirement | Lifestyle | Cherry Tan | [6 empty] | 8 | 2025-10-06 | 2025-10-10 | [5 empty] | 8 | 8 | 2025-10-10
Min Fei | 2025-10-13 |  |  | Fastpath | FG13 OCR Recognize Error Check | Lifestyle | Yan Ren | [6 empty] | 2 | 2025-10-06 | 2025-10-10 | [5 empty] | 2 | 2 | 2025-10-10
Min Fei | 2025-10-13 |  |  | Fastpath | FIV Upload SharePoint Error Check | Lifestyle | Yan Ren | [6 empty] | 2 | 2025-10-06 | 2025-10-10 | [5 empty] | 2 | 2 | 2025-10-10
Min Fei | 2025-10-13 |  |  | Fastpath | ARSC Phase2 Requirement Test And Publish | Lifestyle | Yuki Li | [6 empty] | 2 | 2025-10-06 | 2025-10-10 | [5 empty] | 2 | 2 | 2025-10-10
Min Fei | 2025-10-13 |  |  | Fastpath | Wiki Update About Sales Plan And SharePoint Info Collect | Lifestyle | James Duan | [6 empty] | 2 | 2025-10-06 | 2025-10-10 | [5 empty] | 2 | 2 | 2025-10-10
Min Fei | 2025-10-07 |  |  | SPS 2.0 | Fabric Mill MasterData | Lifestyle | Bin Wu | [6 empty] | 24 | 2025-10-06 | 2025-10-17 |  |  |  |  | 16 | 8 | 24 | 2025-10-17
Min Fei | 2025-10-13 |  |  | Forwarder Invoice | Upload SharePoint Interim Fix And Batch Upload SharePoint API Develop | Lifestyle | Yuki Li | [6 empty] | 16 | 2025-10-13 | 2025-10-17 | [5 empty] | 24 | 24 | 2025-10-17
Min Fei | 2025-10-20 |  |  | Sales Plan | TSK Exception Check and Clean Database | Lifestyle | Jassie Zhou | [6 empty] | 4 | 2025-10-13 | 2025-10-17 | [5 empty] | 4 | 4 | 2025-10-17
Min Fei | 2025-10-20 |  |  | Courier Invoice | Upload SharePoint Verification method Update | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-10-13 | 2025-10-17 | [5 empty] | 4 | 4 | 2025-10-17
Min Fei | 2025-10-27 |  |  | Courier Invoice | Not Running Problem Check | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-10-20 | 2025-10-24 | [5 empty] | 4 | 4 | 2025-10-24
Min Fei | 2025-10-27 |  |  | Forwarder Invoice | Fixed Issues And OCR Error | Lifestyle | Yan Ren | [6 empty] | 6 | 2025-10-20 | 2025-10-24 | [5 empty] | 6 | 6 | 2025-10-24
Min Fei | 2025-10-27 |  |  | VapQuotation | Approve Error Check | Lifestyle | Jenny Chen | [6 empty] | 2 | 2025-10-20 | 2025-10-24 | [5 empty] | 2 | 2 | 2025-10-24
Min Fei | 2025-10-07 |  |  | Mail Tools | Denim Anti-Corruption Requirement | Lifestyle | Lynn Wang | [6 empty] | 8 | 2025-10-20 | 2025-10-24 | [5 empty] | 8 | 8 | 2025-10-24
Min Fei | 2025-10-07 |  |  | SPS 2.0 | Fixed Release To SO Issues | Lifestyle | Cherry Tan | [6 empty] | 8 | 2025-10-20 | 2025-10-24 |  |  |  |  | 4 | 4 | 8 | 2025-10-31
Min Fei | 2025-10-20 |  |  | Forwarder Invoice | Exchange rate conversion Function Update | Lifestyle | James Duan | [6 empty] | 16 | 2025-10-27 | 2025-10-31 | [5 empty] | 16 | 16 | 2025-10-31
Min Fei | 2025-11-03 |  |  | FIV、CIV | Permission Issues Check and Fixed | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-10-27 | 2025-10-31 | [5 empty] | 4 | 4 | 2025-10-31
Min Fei | 2025-11-03 |  |  | Courier Invoice | Fixed Intimate VendorName Error Issues | Intimate | Yan Ren | [6 empty] | 4 | 2025-10-27 | 2025-10-31 | [5 empty] | 4 | 4 | 2025-10-31
Min Fei | 2025-09-22 |  |  | SOH-H&M | Packing List PDF Multi-column Handling | Intimate | JiaJing Wu | [6 empty] | 8 | 2025-10-20 | 2025-10-24 |  | 2025-10-31 | 1 |  | 16 | 4 | 20 | 2025-10-31
Min Fei | 2025-10-27 |  |  | Forwarder Invoice | Enh. Requirement | Lifestyle | Yan Ren | [6 empty] | 8 | 2025-11-03 | 2025-11-07 | [5 empty] | 8 | 8 | 2025-11-07
Min Fei | 2025-11-10 |  |  | SOH-H&M | FNB1 Multi-column Handling Program Update & Test | Intimate | JiaJing Wu | [6 empty] | 8 | 2025-11-03 | 2025-11-07 | [5 empty] | 10 | 10 | 2025-11-07
Min Fei | 2025-11-10 |  |  | Forwarder Invoice | QAS Submit Error Check | Lifestyle | Yan Ren | [6 empty] | 2 | 2025-11-03 | 2025-11-07 | [5 empty] | 2 | 2 | 2025-11-07
Min Fei | 2025-11-03 |  |  | SPS 2.0 | Requirement Issues | Lifestyle | Cherry Tan | [6 empty] | 20 | 2025-11-03 | 2025-11-14 |  |  |  |  | 12 | 8 | 20 | 2025-11-14
Min Fei | 2025-11-18 |  |  | Forwarder Invoice | GetInvoiceReportGridDataSource Interface Optimization | Lifestyle | Yuki Li | [6 empty] | 8 | 2025-11-10 | 2025-11-14 | [5 empty] | 8 | 8 | 2025-11-14
Min Fei | 2025-11-18 |  |  | Forwarder Invoice | Intimate Invoice Ecm Link Missing Check | Lifestyle | Yan Ren | [6 empty] | 4 | 2025-11-10 | 2025-11-14 | [5 empty] | 4 | 4 | 2025-11-14
Min Fei | 2025-11-18 |  |  | SOH-H&M | Program No Running Check | Intimate | JiaJing Wu | [6 empty] | ２ | 2025-11-10 | 2025-11-14 | [5 empty] | 2 | 2 | 2025-11-14
Min Fei | 2025-11-18 |  |  | SPS2.0、Sonarqube | Meeting | Lifestyle | [7 empty] | 4 | 2025-11-10 | 2025-11-14 | [5 empty] | 4 | 4 | 2025-11-14
Min Fei | 2025-11-17 |  |  | SPS 2.0 | Fabric Mill API | Lifestyle | Chloe Zhan | [6 empty] | 32 | 2025-11-10 | 2025-11-21 |  |  |  |  | 16 | 16 | 32 | 2025-11-21
Min Fei | 2025-11-24 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 8 | 2025-11-17 | 2025-11-21 | [5 empty] | 8 | 8 | 2025-11-21
Min Fei | 2025-11-24 |  |  | SPS 2.0 | Check And Fixed QAS Error | Lifestyle | Cherry Tan | [6 empty] | 8 | 2025-11-17 | 2025-11-21 | [5 empty] | 8 | 8 | 2025-11-21
Min Fei | 2025-11-24 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 8 | 2025-11-24 | 2025-11-28 | [5 empty] | 8 | 8 | 2025-11-28
Min Fei | 2025-12-01 |  |  | Forwarder Invoice | PRD Mapping Update | Lifestyle | Yan Ren | [6 empty] | 1 | 2025-11-24 | 2025-11-28 | [5 empty] | 1 | 1 | 2025-11-28
Min Fei | 2025-12-01 |  |  | SOH-H&M | FNB1 Logic Update | Lifestyle | JiaJing Wu | [6 empty] | 8 | 2025-11-24 | 2025-11-28 | [5 empty] | 8 | 8 | 2025-11-28
Min Fei | 2025-12-01 |  |  | SPS 2.0 | FM SAP API Update | Lifestyle | Chloe Zhan | [6 empty] | 24 | 2025-11-24 | 2025-11-28 | [5 empty] | 24 | 24 | 2025-11-28
Min Fei | 2025-11-24 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 8 | 2025-12-01 | 2025-12-05 | [5 empty] | 4 | 4 | 2025-12-05
Min Fei | 2025-09-29 |  |  | SPS 2.0 | Fixed Report Issues | Lifestyle | Cherry Tan | [6 empty] | 32 | 2025-11-24 | 2025-12-05 |  |  |  |  | 24 | 12 | 36 | 2025-12-05
Min Fei | 2025-12-01 |  |  | SPS 2.0 | FM Frontend API Development | Lifestyle | Chloe Zhan | [6 empty] | 16 | 2025-12-01 | 2025-12-05 | [5 empty] | 16 | 16 | 2025-12-05
Min Fei | 2025-12-08 |  |  | SPS 2.0 | Status & Shipment Projection Report Differentiate data Requirement | Lifestyle | Cherry Tan | [6 empty] | 4 | 2025-12-01 | 2025-12-05 | [5 empty] | 4 | 4 | 2025-12-05
Min Fei | 2025-12-08 |  |  | SOH-H&M | Fastpath - Program & Mapping Update and Release | Lifestyle | JiaJing Wu | [6 empty] | 4 | 25-21-1 | 2025-12-05 | [5 empty] | 4 | 4 | 2025-12-05
Min Fei | 2025-11-24 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 4 | 2025-12-08 | 2025-12-12 | [5 empty] | 4 | 4 | 2025-12-12
Min Fei | 2025-10-13 |  |  | Sales Plan | App Service Health Check Develop | Lifestyle | James Duan | [6 empty] | 16 | 2025-12-08 | 2025-12-12 | [5 empty] | 16 | 16 | 2025-12-12
Min Fei | 2025-12-15 |  |  | AR Settlement Clearing | BankStatement No Match Check | Lifestyle | Yuki Li | [6 empty] | 4 | 2025-12-08 | 2025-12-12 | [5 empty] | 4 | 4 | 2025-12-12
Min Fei | 2025-12-15 |  |  | Forwarder Invoice | OCR Result No Match Check And Company Mapping Update | Lifestyle | Yan Ren | [6 empty] | 2 | 2025-12-08 | 2025-12-12 | [5 empty] | 2 | 2 | 2025-12-12
Min Fei | 2025-12-15 |  |  | API Check | FVB API Check | Lifestyle | James Duan | [6 empty] | 8 | 2025-12-15 | 2025-12-19 | [5 empty] | 16 | 16 | 2025-12-19
Min Fei | 2025-12-22 |  |  | Forwarder Invoice | Intimate PRD HK API Error Check | Intimate | Yan Ren | [6 empty] | 4 | 2025-12-15 | 2025-12-19 | [5 empty] | 4 | 4 | 2025-12-19
Min Fei | 2025-12-22 |  |  | Forwarder Invoice | PRD FG16 OCR Update & QAS Vendor Mapping Update | Lifestyle | Yan Ren | [6 empty] | 2 | 2025-12-15 | 2025-12-19 | [5 empty] | 2 | 2 | 2025-12-19
Min Fei | 2025-12-22 |  |  | AR Settlement Clearing | Bankstatement Match Check | Lifestyle | Lynn Wang | [6 empty] | 2 | 2025-12-15 | 2025-12-19 | [5 empty] | 2 | 2 | 2025-12-19
Min Fei | 2025-12-22 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 4 | 2025-12-15 | 2025-12-19 | [5 empty] | 4 | 4 | 2025-12-19
Min Fei | 2025-12-22 |  |  | API Check | FVB API Check Optimization | Lifestyle | James Duan | [6 empty] | 2 | 2025-12-22 | 2025-12-26 | [5 empty] | 2 | 2 | 2025-12-26
Min Fei | 2025-12-22 |  |  | AR Settlement Clearing | Add New Customer Requirement | Lifestyle | Lynn Wang | [6 empty] | ８ | 2025-12-22 | 2025-12-26 | [5 empty] | 8 | 8 | 2025-12-26
Min Fei | 2025-12-29 |  |  | Forwarder Invoice | FG25 Template Update | Lifestyle | Yan Ren | [6 empty] | 6 | 2025-12-22 | 2025-12-26 | [5 empty] | 4 | 4 | 2025-12-26
Min Fei | 2025-12-15 |  |  | SPS 2.0 | FM API About SO | Lifestyle | Chloe Zhan | [6 empty] | 24 | 2025-12-22 | 2025-12-26 |  | 2025-12-26 | 1 |  |  | 24 | 24 | 2025-12-26
Min Fei | 2025-12-22 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 4 | 2025-12-22 | 2025-12-26 | [5 empty] | 4 | 4 | 2025-12-26
Min Fei | 2025-12-15 |  |  | Holiday | 元旦 | Lifestyle | [7 empty] | 8 | 2025-12-29 | 2026-01-02 | [5 empty] | 8 | 8 | 2026-01-02
Min Fei | 2025-12-15 |  |  | Sales Plan | SCC Functino ID Replace | Lifestyle | James Duan | [6 empty] | 2 | 2025-12-29 | 2026-01-02 | [5 empty] | 2 | 2 | 2026-01-02
Min Fei | 2026-01-05 |  |  | AR Settlement Clearing | New Requirement Release and Test | Lifestyle | Lynn Wang | [6 empty] | 2 | 2025-12-29 | 2026-01-02 | [5 empty] | 2 | 2 | 2026-01-02
Min Fei | 2026-01-05 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 4 | 2025-12-29 | 2026-01-02 | [5 empty] | 4 | 4 | 2026-01-02

## Completed - 2026
Developer | Report Date | Project ID | CHARM No. | Program Title | Program Description | Initiated Company (Denim, CKL, Sweater, Intimate, T-Shirt, T-Shirt & Sweater) | Requested By | Advised By | This Week | Next Week 1 | Next Week 2 | Next Week 3 | Over 4 Week | Total Man Hrs per Program | Plan Start Date | Plan Completion Date | Revised Start Date | Revised COM Date | No. of times on Revise COM Date | User request Completion Date | Last Week Cumulated Man Hrs | Weekly allocated Man Hrs | Allocated Man Hrs | Actual COM Date | Remark | Functional Team Expected Development Date | Outsource | Priority | F/S ready date | F/S URL | F/S Confirm or Not? | F/S Confirm Date
Min Fei | 2025-12-15 |  |  | Holiday | 元旦 | Lifestyle | [7 empty] | 8 | 2025-12-29 | 2026-01-02 | [5 empty] | 8 | 8 | 2026-01-02
Min Fei | 2025-12-15 |  |  | Sales Plan | SCC Functino ID Replace | Lifestyle | James Duan | [6 empty] | 2 | 2025-12-29 | 2026-01-02 | [5 empty] | 2 | 2 | 2026-01-02
Min Fei | 2026-01-05 |  |  | AR Settlement Clearing | New Requirement Release and Test | Lifestyle | Lynn Wang | [6 empty] | 2 | 2025-12-29 | 2026-01-02 | [5 empty] | 2 | 2 | 2026-01-02
Min Fei | 2026-01-05 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 4 | 2025-12-29 | 2026-01-02 | [5 empty] | 4 | 4 | 2026-01-02
Min Fei | 2025-12-29 |  |  | SOH-H&M | Purchase Order No Match Country Breakdowm Fixed | Intimate | JiaJing Wu | [6 empty] | 10 | 2026-01-05 | 2026-01-09 | [5 empty] | 10 | 10 | 2026-01-09
Min Fei | 2025-12-29 |  |  | SPS 2.0 | FM Sales Shipment Report | Lifestyle | Chloe Zhan | [6 empty] | 16 | 2025-12-29 | 2026-01-09 |  |  |  |  | 8 | 8 | 16 | 2026-01-09
Min Fei | 2025-12-22 |  |  | SPS 2.0 | Report Export Optimization | Lifestyle | Cherry Tan | [6 empty] | 32 | 2025-12-29 | 2026-01-09 |  |  |  |  | 16 | 16 | 32 | 2026-01-09
Min Fei | 2026-01-12 |  |  | Sales Plan | Sales Plan PRD SCC Check | Lifestyle | Jassie Zhou | [6 empty] | 2 | 2025-12-29 | 2026-01-09 | [5 empty] | 2 | 2 | 2026-01-09
Min Fei | 2026-01-05 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 4 | 2026-01-05 | 2026-01-09 | [5 empty] | 4 | 4 | 2026-01-09
Min Fei | 2026-01-05 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 2 | 2026-01-12 | 2026-01-16 | [5 empty] | 2 | 2 | 2026-01-16
Min Fei | 2026-01-19 |  |  | Forwarder Invoice | Vendor Mapping Table Update | Lifestyle | Yan Ren | [6 empty] | 2 | 2026-01-12 | 2026-01-16 | [5 empty] | 2 | 2 | 2026-01-16
Min Fei | 2026-01-19 |  |  | Forwarder Invoice | FG51 Repeat Error Check | Lifestyle | Yan Ren | [6 empty] | 4 | 2026-01-12 | 2026-01-16 | [5 empty] | 4 | 4 | 2026-01-16
Min Fei | 2026-01-19 |  |  | SPS 2.0 | PRD Environment Status Report Export Error Fixed | Lifestyle | Cherry Tan | [6 empty] | 8 | 2026-01-12 | 2026-01-16 | [5 empty] | 8 | 8 | 2026-01-16
Min Fei | 2026-01-19 |  |  | Sales Plan | PRD Environment Error Check and Fixed | Lifestyle | Jassie Zhou | [6 empty] | 4 | 2026-01-12 | 2026-01-16 | [5 empty] | 4 | 4 | 2026-01-16
Min Fei | 2026-01-19 |  |  | FVB | FVB Training | Lifestyle | Smile Chow | [6 empty] | 4 | 2026-01-12 | 2026-01-16 | [5 empty] | 4 | 4 | 2026-01-16
Min Fei | 2026-01-05 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 2 | 2026-01-12 | 2026-01-16 | [5 empty] | 2 | 2 | 2026-01-23
Min Fei | 2024-12-23 |  |  | Group eForm | Study | LifeStyle | Bin Wu | [6 empty] | 24 | 2026-01-12 | 2026-01-23 |  |  |  |  | 8 | 16 | 24 | 2026-01-23
Min Fei | 2026-01-19 |  |  | SPS 2.0 | Intimate Shipment Projection Report Issue | Lifestyle | Lydia Gao | [6 empty] | 8 | 2026-01-19 | 2026-01-23 | [5 empty] | 8 | 8 | 2026-01-23
Min Fei | 2026-01-12 |  |  | SOH-H&M | Purchase Order OCR Identify Enh. | Intimate | JiaJing Wu | [6 empty] | 16 | 2026-01-19 | 2026-01-30 |  |  |  |  | 8 | 8 | 16 | 2026-01-23
Min Fei | 2026-01-19 |  |  | Group eForm | Issues Practice | Lifestyle | Bin Wu | [6 empty] | 16 | 2026-01-19 | 2026-01-23 | [5 empty] | 8 | 8 | 2026-01-23
Min Fei | 2026-01-05 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 2 | 2026-01-26 | 2026-01-30 | [5 empty] | 2 | 2 | 2026-01-30
Min Fei | 2025-11-03 |  |  | Forwarder Invoice | Approve in External Network Test | Lifestyle | Yuki Li | [6 empty] | 2 | 2026-01-26 | 2026-01-30 | [5 empty] | 2 | 2 | 2026-01-30
Min Fei | 2026-02-02 |  |  | Sales Plan | Handle PRD Email Service Error And Clean Data | Lifestyle | Jassie Zhou | [6 empty] | 4 | 2026-01-26 | 2026-01-30 | [5 empty] | 4 | 4 | 2026-01-30
Min Fei | 2026-02-02 |  |  | Forwarder Invoice | FG13、FG51、FG53 Error Check | Lifestyle | Yan Ren | [6 empty] | 2 | 2026-01-26 | 2026-01-30 | [5 empty] | 2 | 2 | 2026-01-30
Min Fei | 2026-02-02 |  |  | Forwarder Invoice | Intimate Job Error Check | Intimate | Yan Ren | [6 empty] | 1 | 2026-01-26 | 2026-01-30 | [5 empty] | 1 | 1 | 2026-01-30
Min Fei | 2026-02-02 |  |  | SPS 2.0 | Intimate Report Backup Check | Intimate | Lydia Gao | [6 empty] | 1 | 2026-01-26 | 2026-01-30 | [5 empty] | 1 | 1 | 2026-01-30
Min Fei | 2026-01-05 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 2 | 2026-02-02 | 2026-02-06 | [5 empty] | 2 | 2 | 2026-02-06
Min Fei | 2026-01-26 |  |  | SOH.LaunchPad | Study and Fixed Issues | Lifestyle | James Duan | [6 empty] | 24 | 2026-01-26 | 2026-02-06 |  |  |  |  | 12 | 16 | 16 | 2026-02-06
Min Fei | 2026-02-09 |  |  | Forwarder Invoice | FG17 Template Error Check And Update | Lifestyle | Yan Ren | [6 empty] | 8 | 2026-02-02 | 2026-02-06 | [5 empty] | 8 | 8 | 2026-02-06
Min Fei | 2026-02-09 |  |  | OCR_Adidas | Adidas OCR FNC01 Template Enh. | Lifestyle | Beck Zhang | [6 empty] | 6 | 2026-02-02 | 2026-02-06 | [5 empty] | 6 | 6 | 2026-02-06
Min Fei | 2026-02-25 |  |  | Meeting | FM API Meeting | Lifestyle | [7 empty] | 4 | 2026-02-09 | 2026-02-13 | [5 empty] | 4 | 4 | 2026-02-13
Min Fei | 2026-02-25 |  |  | SPS 2.0 | FM About API | Lifestyle | Chloe Zhan | [6 empty] | 12 | 2026-02-09 | 2026-02-13 | [5 empty] | 16 | 16 | 2026-02-13
Min Fei | 2026-02-25 |  |  | Forwarder Invoice | FG23 & FG24 Template Error Check And Update | Lifestyle | Yan Ren | [6 empty] | 8 | 2026-02-09 | 2026-02-13 | [5 empty] | 8 | 8 | 2026-02-13
Min Fei | 2026-02-25 |  |  | VapQuotation & CIV | SCC FunctionID Update | Lifestyle | Jenny Chen | [6 empty] | 2 | 2026-02-09 | 2026-02-13 | [5 empty] | 2 | 2 | 2026-02-13
Min Fei | 2026-02-25 |  |  | Courier Invoice | Job Not Running Error Check | Lifestyle | Yan Ren | [6 empty] | 2 | 2026-02-09 | 2026-02-13 | [5 empty] | 2 | 2 | 2026-02-13
Min Fei | 2026-02-25 |  |  | SPS 2.0 | Urgent Issue | Lifestyle | Cherry Tan | [6 empty] | 8 | 2026-02-09 | 2026-02-13 | [5 empty] | 8 | 8 | 2026-02-13
Min Fei | 2026-03-02 |  |  | Forwarder Invoice | Intimate SCC FunctionID Update | Intimate | Yuki Li | [6 empty] | 2 | 2026-02-23 | 2026-02-27 | [5 empty] | 2 | 2 | 2026-02-27
Min Fei | 2026-01-12 |  |  | Holiday | 春节 | Lifestyle | [7 empty] | 56 | 2026-02-16 | 2026-02-27 |  |  |  |  | 40 | 16 | 56 | 2026-02-27
Min Fei | 2026-02-02 |  |  | SPS 2.0 | Intimate Shipment Report Issues | Intimate | Lydia Gao | [6 empty] | 24 | 2026-02-23 | 2026-02-27 | [5 empty] | 16 | 24 | 2026-02-27
Min Fei | 2026-03-02 |  |  | Forwarder Invoice | FG15 Template Error Check And Update | Lifestyle | Yan Ren | [6 empty] | 8 | 2026-02-23 | 2026-02-27 | [5 empty] | 8 | 8 | 2026-02-27
Min Fei | 2026-03-09 |  |  | Forwarder Invoice | FG15 Template Update | Lifestyle | Yan Ren | [6 empty] | 6 | 2026-03-02 | 2026-03-06 | [5 empty] | 8 | 8 | 2026-03-06
Min Fei | 2026-03-09 |  |  | SPS 2.0 | FM NewCostBreakdown API Integration testing | Lifestyle | Chloe Zhan | [6 empty] | 8 | 2026-03-02 | 2026-03-06 | [5 empty] | 8 | 8 | 2026-03-06
Min Fei | 2026-03-09 |  |  | OCR | OCR Task Running Slow Check | Lifestyle | [7 empty] | 16 | 2026-03-02 | 2026-03-06 | [5 empty] | 14 | 14 | 2026-03-06
Min Fei | 2026-03-09 |  |  | Group eForm | Incorrect Budget Amount Update | Lifestyle | Victor Cheung | [6 empty] | 2 | 2026-03-02 | 2026-03-06 | [5 empty] | 2 | 2 | 2026-03-06
Min Fei | 2026-01-26 |  |  | Group eForm | Fixed Issues | Lifestyle | Victor Cheung | [6 empty] | 32 | 2026-01-26 | 2026-03-06 |  |  |  |  | 24 | 8 | 32 | 2026-03-06
Min Fei | 2026-01-05 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 2 | 2026-03-09 | 2026-03-13 | [5 empty] | 2 | 2 | 2026-03-13
Min Fei | 2026-03-09 |  |  | SPS 2.0 | Update Project Enh. | Lifestyle | Cherry Tan | [6 empty] | 12 | 2026-03-09 | 2026-03-13 | [5 empty] | 16 | 16 | 2026-03-13
Min Fei | 2026-03-16 |  |  | SPS 2.0 | FM SPS InventoryBalance API Update | Lifestyle | Chloe Zhan | [6 empty] | 4 | 2026-03-09 | 2026-03-13 | [5 empty] | 4 | 4 | 2026-03-13
Min Fei | 2026-03-16 |  |  | Courier Invoice | Update Permission And Summary Report Check | Lifestyle | Yan Ren | [6 empty] | 4 | 2026-03-09 | 2026-03-13 | [5 empty] | 2 | 2 | 2026-03-13
Min Fei | 2026-03-09 |  |  | SPS 2.0 | FM SPS DisposalResult to SAP API | Lifestyle | Chloe Zhan | [6 empty] | 12 | 2026-03-09 | 2026-03-13 | [5 empty] | 12 | 12 | 2026-03-13
Min Fei | 2026-03-16 |  |  | Sales Plan | Urgent Enh. | Lifestyle | Jassie Zhou | [6 empty] | 12 | 2026-03-16 | 2026-03-20 |  |  |  |  | 4 | 8 | 12 | 2026-03-20
Min Fei | 2026-03-16 |  |  | SPS 2.0 | FM Interface | Lifestyle | Chloe Zhan | [6 empty] | 8 | 2026-03-16 | 2026-03-20 |  |  |  |  | 8 | 8 | 8 | 2026-03-20
Min Fei | 2026-01-12 |  |  | Leave | 请假 | Lifestyle | [7 empty] | 24 | 2026-03-16 | 2026-03-20 |  |  |  |  | 24 | 24 | 24 | 2026-03-20
Min Fei | 2026-03-23 |  |  | OCR_Adidas | OCR Error Check And Update | Lifestyle | Beck Zhang | [6 empty] | 12 | 2026-03-23 | 2026-03-27 | [5 empty] | 12 | 12 | 2026-03-27
Min Fei | 2026-03-23 |  |  | Forwarder Invoice | FIV PDF Upload Not Responding Check | Lifestyle | Yan Ren | [6 empty] | 4 | 2026-03-23 | 2026-03-27 | [5 empty] | 4 | 4 | 2026-03-27
Min Fei | 2026-03-23 |  |  | SPS 2.0 | PRD Issues | Lifestyle | Cherry Tan | [6 empty] | 16 | 2026-03-23 | 2026-03-27 | [5 empty] | 16 | 16 | 2026-03-27
Min Fei | 2026-03-30 |  |  | Forwarder Invoice | FG25 Template Error Handle | Lifestyle | Yan Ren | [6 empty] | 2 | 2026-03-23 | 2026-03-27 | [5 empty] | 2 | 2 | 2026-03-27
Min Fei | 2026-03-30 |  |  | SPS 2.0 | FM Receive Disposal API Development And Testing | Lifestyle | Chloe Zhan | [6 empty] | 8 | 2026-03-23 | 2026-03-27 | [5 empty] | 8 | 8 | 2026-03-27
Min Fei | 2026-03-23 |  |  | SPS 2.0 | PRD Issues | Lifestyle | Sunye Liu | [6 empty] | 4 | 2026-03-30 | 2026-04-03 | [5 empty] | 4 | 4 | 2026-04-03
Min Fei | 2026-03-09 |  |  | SOH.LaunchPad | CVC eDO & GR Issues | Lifestyle | Lucia Wang | [6 empty] | 8 | 2026-03-09 | 2026-03-13 |  | 2026-04-03 | 1 |  |  | 8 | 8 | 2026-04-03
Min Fei | 2026-03-30 |  |  | Group eForm | Office eForm Enh. | Lifestyle | Victor Cheung | [6 empty] | 16 | 2026-03-30 | 2026-04-03 | [5 empty] | 16 | 16 | 2026-04-03
Min Fei | 2026-03-30 |  |  | SPS 1.0 | EIL - Status Report Logic Update | Lifestyle | Jenny Chen | [6 empty] | 8 | 2026-03-30 | 2026-04-03 | [5 empty] | 8 | 8 | 2026-04-03
Min Fei | 2026-02-02 |  |  | Forwarder Invoice | Fixed Issues & Enh. | Lifestyle | Yan Ren | [6 empty] | 16 | 2026-03-30 | 2026-04-03 |  | 2026-04-10 | 1 |  | 4 | 12 | 12 | 2026-04-10
Min Fei | 2026-03-16 |  |  | Holiday | 清明节 | Lifestyle | [7 empty] | 8 | 2026-04-06 | 2026-04-10 | [5 empty] | 8 | 8 | 2026-04-10
Min Fei | 2026-04-13 |  |  | SPS 2.0 | Status Report 1.0 Value Check And Update | Lifestyle | Cherry Tan | [6 empty] | 12 | 2026-04-06 | 2026-04-10 | [5 empty] | 12 | 12 | 2026-04-10
Min Fei | 2026-04-13 |  |  | Group eForm | QAS Export Budget Category Error | Lifestyle | Victor Cheung | [6 empty] | 2 | 2026-04-06 | 2026-04-10 | [5 empty] | 2 | 2 | 2026-04-10
Min Fei | 2026-04-13 |  |  | SPS 2.0 | Copy Function Enhance | Lifestyle | Jenny Chen | [6 empty] | 16 | 2026-04-13 | 2026-04-17 | [5 empty] | 8 | 8 | 2026-04-17
Min Fei | 2026-04-13 |  |  | SPS 1.0 | EIL - Update Function Enhance | Lifestyle | Cherry Tan | [6 empty] | 8 | 2026-04-13 | 2026-04-17 | [5 empty] | 16 | 16 | 2026-04-17
Min Fei | 2026-04-20 |  |  | SPS 2.0 | Add Rule_GenerateSO | Lifestyle | Smile Chow | [6 empty] | 1 | 2026-04-13 | 2026-04-17 | [5 empty] | 1 | 1 | 2026-04-17
Min Fei | 2026-04-20 |  |  | CIV | Invoice Not Handle Check | Lifestyle | Yuki Li | [6 empty] | 3 | 2026-04-13 | 2026-04-17 | [5 empty] | 3 | 3 | 2026-04-17
Min Fei | 2026-04-20 |  |  | SPS 2.0 | API Meeting | Lifestyle | Chloe Zhan | [6 empty] | 2 | 2026-04-13 | 2026-04-17 | [5 empty] | 2 | 2 | 2026-04-17
Min Fei | 2026-03-23 |  |  | Forwarder Invoice | FG54 New Template And Test | Lifestyle | Yan Ren | [6 empty] | 8 | 2026-04-20 | 2026-04-24 | [5 empty] | 12 | 12 | 2026-04-24
Min Fei | 2026-04-27 |  |  | Courier Invoice | CIV Job Error Check And Handle | Lifestyle | Yuki Li | [6 empty] | 4 | 2026-04-20 | 2026-04-24 | [5 empty] | 4 | 4 | 2026-04-24
Min Fei | 2026-04-27 |  |  | SPS 2.0 | Add Rule_GenerateSO & GenerateSO Error Check | Lifestyle | Smile Chow | [6 empty] | 2 | 2026-04-20 | 2026-04-24 | [5 empty] | 2 | 2 | 2026-04-24
Min Fei | 2026-04-27 |  |  | SPS 2.0 | Add Status Report Mapping | Lifestyle | Cherry Tan | [6 empty] | 2 | 2026-04-20 | 2026-04-24 | [5 empty] | 2 | 2 | 2026-04-24
Min Fei | 2026-04-20 |  |  | SPS 2.0 | Status Report Auto Send & 1.0 Value Check And Update | Lifestyle | Cherry Tan | [6 empty] | 16 | 2026-04-13 | 2026-04-24 |  |  |  |  | 4 | 10 | 14 | 2026-04-24
Min Fei | 2026-04-27 |  |  | AR Settlement Clearing | Payment Advice Upload Error Check | Lifestyle | Yuki Li | [6 empty] | 4 | 2026-04-20 | 2026-04-24 | [5 empty] | 4 | 4 | 2026-04-24
Min Fei | 2026-05-05 |  |  | Meeting | FIV BD Meeting | Lifestyle | Yan Ren | [6 empty] | 2 | 2026-04-27 | 2026-05-01 | [5 empty] | 2 | 2 | 2026-05-01
Min Fei | 2026-05-05 |  |  | Group eForm | PRD Issues - Not Release PO | Lifestyle | Victor Cheung | [6 empty] | 4 | 2026-04-27 | 2026-05-01 | [5 empty] | 4 | 4 | 2026-05-01
Min Fei | 2026-04-27 |  |  | SPS 2.0 | Issues And Enh. | Lifestyle | Cherry Tan | [6 empty] | 8 | 2026-04-20 | 2026-05-01 |  |  |  |  | 6 | 18 | 24 | 2026-05-01
Min Fei | 2026-05-05 |  |  | SPS 2.0 | Intimate Shipmen Projection Report BackUp Check | Lifestyle | Lydia Gao | [6 empty] | 2 | 2026-04-27 | 2026-05-01 | [5 empty] | 2 | 2 | 2026-05-01
Min Fei | 2026-05-05 |  |  | OCR_Adidas | OCR Error Check | Lifestyle | Beck Zhang | [6 empty] | 2 | 2026-04-27 | 2026-05-01 | [5 empty] | 2 | 2 | 2026-05-01
Min Fei | 2026-04-13 |  |  | Holiday | 劳动节 | Lifestyle | [7 empty] | 16 | 2026-04-27 | 2026-05-08 |  |  |  |  | 8 | 8 | 16 | 2026-05-08
Min Fei | 2026-04-13 |  |  | Sales Plan | Enh. | Lifestyle | Jassie Zhou | [6 empty] | 8 | 2026-04-13 | 2026-05-01 |  | 2026-05-08 | 1 |  | 4 | 4 | 8 | 2026-05-08
Min Fei | 2026-04-27 |  |  | OCR | OCR New PDF Test | Lifestyle | James Duan | [6 empty] | 4 | 2026-04-27 | 2026-05-01 | 2026-05-04 | 2026-05-08 | 1 |  |  | 6 | 6 | 2026-05-08
Min Fei | 2026-05-11 |  |  | Sales Plan | PRD Detail Unabel To View And Approver Not Data Check | Lifestyle | Jassie Zhou | [6 empty] | 4 | 2026-05-04 | 2026-05-08 | [5 empty] | 4 | 4 | 2026-05-08
Min Fei | 2026-05-11 |  |  | SPS 1.0 | EIL - 800 Update SPS_Hdr Table Data | Lifestyle | Jenny Chen | [6 empty] | 4 | 2026-05-04 | 2026-05-08 | [5 empty] | 4 | 4 | 2026-05-08
Min Fei | 2026-05-11 |  |  | SOH.LaunchPad | CVC eDO & GR Issues | Lifestyle | Rachel Chen | [6 empty] | 4 | 2026-05-04 | 2026-05-08 | [5 empty] | 4 | 4 | 2026-05-08
Min Fei | 2026-05-11 |  |  | SPS 1.0 & 2.0 | PRD Issues Check And Fixed | Lifestyle | Cherry Tan | [6 empty] | 4 | 2026-05-04 | 2026-05-08 | [5 empty] | 4 | 4 | 2026-05-08
Min Fei | 2026-01-05 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 4 | 2026-05-11 | 2026-05-15 | [5 empty] | 4 | 4 | 2026-05-15
Min Fei | 2026-04-27 |  |  | SPS 2.0 | Shipment Project Web API | Lifestyle | Max Chen | [6 empty] | 8 | 2026-04-27 | 2026-05-01 | 2026-05-11 | 2026-05-15 | 1 |  |  | 8 | 8 | 2026-05-15
Min Fei | 2026-03-30 |  |  | SPS 2.0 | Intimate Shipmen Projection Report Issues And Enh. | Lifestyle | Lydia Gao | [6 empty] | 16 | 2026-04-20 | 2026-05-01 | 2026-05-11 | 2026-05-15 | 1 |  |  | 16 | 16 | 2026-05-15
Min Fei | 2026-05-11 |  |  | SPS 2.0 | Status Report PRD Issues | Lifestyle | Cherry Tan | [6 empty] | 6 | 2026-05-11 | 2026-05-15 | [5 empty] | 6 | 6 | 2026-05-15
Min Fei | 2026-05-11 |  |  | SPS 1.0 | EIL - 800 Update SPS_Hdr Table Data | Lifestyle | Jenny Chen | [6 empty] | 2 | 2026-05-11 | 2026-05-15 | [5 empty] | 2 | 2 | 2026-05-15
Min Fei | 2026-05-11 |  |  | Group eForm | Offeice PO PRD Error Check And Fixed | Lifestyle | Victor Cheung | [6 empty] | 4 | 2026-05-18 | 2026-05-22 | [5 empty] | 4 | 4 | 2026-05-22
Min Fei | 2026-05-11 |  |  | SPS 2.0 | ShipmentProjection API Check | Lifestyle | Harry Huang | [6 empty] | 2 | 2026-05-18 | 2026-05-22 | [5 empty] | 2 | 2 | 2026-05-22
Min Fei | 2026-05-11 |  |  | Forwarder Invoice | Mapping Update And Permissions Update | Lifestyle | Yan Ren | [6 empty] | 2 | 2026-05-18 | 2026-05-22 | [5 empty] | 2 | 2 | 2026-05-22
Min Fei | 2026-05-11 |  |  | Sales Plan | Fixed Send Email Error And Email Enh. | Lifestyle | Jassie Zhou | [6 empty] | 4 | 2026-05-18 | 2026-05-22 | [5 empty] | 4 | 4 | 2026-05-22
Min Fei | 2026-05-25 |  |  | SPS 2.0 | Urgent Enh. | Lifestyle | Cherry Tan | [6 empty] | 8 | 2026-05-25 | 2026-05-29 | [5 empty] | 8 | 8 | 2026-05-29
Min Fei | 2026-06-01 |  |  | SPS 2.0 | Intimate ShipmentProjection Report Check | Lifestyle | Lydia Gao | [6 empty] | 4 | 2026-05-25 | 2026-05-29 | [5 empty] | 4 | 4 | 2026-05-29
Min Fei | 2026-01-12 |  |  | Group eForm | Assets PO | Lifestyle | Bin Wu | [6 empty] | 64 | 2026-03-16 | 2026-04-03 |  | 2026-06-05 | 2 |  | 40 | 8 | 48 | 2026-06-05
Min Fei | 2026-06-08 |  |  | SPS 1.0 | Status Report Auto Send Not Data Check | Lifestyle | Cherry Tan | [6 empty] | 4 | 2026-06-01 | 2026-06-05 | [5 empty] | 4 | 4 | 2026-06-05
Min Fei | 2026-03-31 |  |  | SPS 2.0 | Status Report Backup & Enh. | Lifestyle | Cherry Tan | [6 empty] | 32 | 2026-04-27 | 2026-05-01 | 2026-06-01 | 2026-06-12 | 2 |  | 16 | 8 | 24 | 2026-06-12
Min Fei | 2026-04-07 |  |  | SPS 1.0 | CAL - Enh. CPPC_N01_FABRIC_HIST Add SAM per Doz | Lifestyle | Jenny Chen | [6 empty] | 16 | 2026-05-11 | 2026-05-15 | 2026-06-01 | 2026-06-12 | 2 |  |  | 8 | 8 | 2026-06-12
Min Fei | 2026-06-15 |  |  | Group eForm | Fixed Assets PO Merge And Release To QAS | Lifestyle | Victor Cheung | [6 empty] | 4 | 2026-06-08 | 2026-06-12 | [5 empty] | 4 | 4 | 2026-06-12
Min Fei | 2026-06-15 |  |  | SPS 2.0 | Urgency Issues And Enh. | Lifestyle | Cherry Tan | [6 empty] | 8 | 2026-06-08 | 2026-06-12 | [5 empty] | 8 | 8 | 2026-06-12
Min Fei | 2026-06-01 |  |  | Holiday | 端午节 | Lifestyle | [7 empty] | 8 | 2026-06-15 | 2026-06-19 | [5 empty] | 8 | 8 | 2026-06-19
Min Fei | 2026-06-22 |  |  | SPS 2.0 | Status Report FVB Get Value Update | Lifestyle | Cherry Tan | [6 empty] | 4 | 2026-06-15 | 2026-06-19 | [5 empty] | 4 | 4 | 2026-06-19
Min Fei | 2026-05-18 |  |  | AR Settlement Clearing | MS & H&M Enh. | Lifestyle | Yuki | [6 empty] | 8 | 2026-06-22 | 2026-06-26 | [5 empty] | 8 | 8 | 2026-06-26
Min Fei | 2026-06-01 |  |  | SonarQube | SonarQube Local Scan | Lifestyle | James Duan | [6 empty] | 16 | 2026-05-25 | 2026-06-12 |  | 2026-06-26 | 1 |  | 4 | 4 | 8 | 2026-06-26
Min Fei | 2026-06-05 |  |  | Group eForm | Fixed Assets PO Issues | Lifestyle | Victor Cheung | [6 empty] | 40 | 2026-05-01 | 2026-07-03 |  |  |  |  | 40 | 16 | 56 | 2026-07-03
Min Fei | 2026-06-22 |  |  | Leave | 请假 | Lifestyle | [7 empty] | 12 | 2026-06-29 | 2026-07-03 | [5 empty] | 12 | 12 | 2026-07-03
Min Fei | 2026-06-22 |  |  | SPS 2.0 | Urgent Issues & Enh. | Lifestyle | Cherry Tan | [6 empty] | 24 | 2026-06-22 | 2026-06-26 |  | 2026-07-03 | 1 |  |  | 8 | 8 | 2026-07-03
Min Fei | 2026-07-06 |  |  | SPS 2.0 | Fixed Intimate Shipment Report Value Error | Lifestyle | Lydia Gao | [6 empty] | 4 | 2026-06-29 | 2026-07-03 | [5 empty] | 4 | 4 | 2026-07-03
Min Fei | 2026-07-06 |  |  | ARSC | H&M And M&S Enh. With Test | Lifestyle | Yuki Li | [6 empty] | 2 | 2026-06-29 | 2026-07-03 | [5 empty] | 2 | 2 | 2026-07-03
Min Fei | 2026-06-22 |  |  | FIV | FG54 Template Error Check And Update | Lifestyle | Yan Ren | [6 empty] | 6 | 2026-06-22 | 2026-06-26 |  | 2026-07-10 | 1 |  | 4 | 2 | 6 | 2026-07-10
Min Fei | 2026-07-13 |  |  | SPS 2.0 | PRD Auto Status Report Issues | Lifestyle | Cherry Tan | [6 empty] | 2 | 2026-07-06 | 2026-07-10 | [5 empty] | 2 | 2 | 2026-07-10
Min Fei | 2026-07-13 |  |  | SPS 2.0 | PRD Projection Approve SO Error Check | Lifestyle | Cherry Tan | [6 empty] | 4 | 2026-07-06 | 2026-07-10 | [5 empty] | 4 | 4 | 2026-07-10
Min Fei | 2026-07-13 |  |  | FIV & CIV | Mapping Update | Lifestyle | Yan & Yuki | [6 empty] | 2 | 2026-07-06 | 2026-07-10 | [5 empty] | 2 | 2 | 2026-07-10
Min Fei | 2026-07-13 |  |  | Sales Plan | Update Pool Balance And Fixed Reset Budget Issue | Lifestyle | Jassie Zhou | [6 empty] | 4 | 2026-07-06 | 2026-07-10 | [5 empty] | 4 | 4 | 2026-07-10
Min Fei | 2026-07-13 |  |  | SPS 2.0 | Intimate Shipment Projection Report Issues | Lifestyle | Lydia Gao | [6 empty] | 2 | 2026-07-06 | 2026-07-10 | [5 empty] | 2 | 2 | 2026-07-10
Min Fei | 2026-06-29 |  |  | SOH-H&M | Scan Error Check And Fixed | Lifestyle | JiaJing Wu | [6 empty] | 8 | 2026-07-06 | 2026-07-10 |  | 2026-07-17 | 1 |  |  | 4 | 8 | 2026-07-17
Min Fei | 2026-07-20 |  |  | SPS 2.0 | Urgency Issues | Lifestyle | Cherry Tan | [6 empty] | 24 | 2026-07-13 | 2026-07-17 | [5 empty] | 24 | 24 | 2026-07-17
Min Fei | 2026-07-20 |  |  | Meeting | Meeting | Lifestyle | [7 empty] | 4 | 2026-07-13 | 2026-07-17 | [5 empty] | 4 | 4 | 2026-07-17